## Timeline
Judul : Prediksi ketersedian padi nasional sebagai upaya meningkatkan ketahanan pangan menggunakan algoritma ARIMA
Nama Kelompok : Swasebada Team
| Project Start Date |  | 2023-05-17 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
| Project Manager |  | Azka Fauzi Al Parisi | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03
 | time axis 2023-05-15 to 2023-07-09
WBS | TASK | Deliverable | PIC | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2023-05-15 to 2023-07-09
1 | Business Analis |  |  |  |  | - |  |  | -
0.1 | Cari topik masing-masing (minimal 1 topik) Topik beserta bussiness understanding dan rencana hasilnya (rekomendasi). Kalo memungkinkan sama datasetnya |  | Dede |  | 2023-05-15 | 2023-05-17 | 3 | 100% | 3
0.1 |  | Prediksi popularitas Aplikasi untuk pengiklanan, Dataset: Aplikasi Google Play store di Kagle | Shintya |  | 2023-05-19 | 2023-05-22 | 4 | 100% | 2
0.1 |  | Prediksi Analisis Ketersediaan Pangan Padi | Azka |  | 2023-05-19 | 2023-05-22 | 4 | 100% | bar: 2023-05-19 to 2023-05-20
0.1 |  | Prediksi tingkat penyebaran covid-19 menggunakan teknik data mining naive bayes | Zeni |  | 2023-05-19 | 2023-05-22 | 4 | 100% | 2
0.1 |  | Peramalan Jumlah Penumpang kereta Api berdasarkan faktor kepuasan | Kevin |  | 2023-05-19 | 2023-05-22 | 4 | 100% | 2
0.1 |  | Implementasi Artificial Inteligence untuk Memprediksi Harga Penjualan Rumah Menggunakan Metode Random Forest dan Flask | Nurulliza |  | 2023-05-19 | 2023-05-22 | 4 | 100% | 2
2 | Data Engineer |  |  |  |  | - |  |  | -
0.1 |  |  | Dede |  | 2018-10-22 | 2018-10-22 |  | 0% | 1
0.1 | Mencari data Luas Provinsi, Jumlah Penduduk |  | Shintya |  | 2023-05-29 | 2023-06-01 | 4 | 100%
0.1 | Data Dari Pdf Ke Excel, menggabungkan data luas panen, luas provinsi, jumlah penduduk, produksi beras, kebutuhan rumah tangga |  | Shintya |  | 2023-06-02 | 2023-06-06 | 5 | 100% | 3
0.1 | Mencari data Harga Beras |  | Zeni |  | 2023-05-29 | 2023-05-29 |  | 100% | 1
0.1 | Mencari Dataset Lama Penyinaran Matahari |  | kevin C |  | 2023-06-08 | 2023-06-09 | 2 | 100% | 2
0.1 | Mencari data produksi beras dan curah hujan |  | Nurulliza Camilla |  | 2023-06-02 | 2023-06-04 | 3 | 100% | 1
3 | Data Modeler |  |  |  |  | - |  |  | -
0.1 | Melakukan pengolahan data berupa, data understanding dan data preparation |  | Azka |  | 2023-06-06 | 2023-06-06 | 1 | 100% | 1 | bar: 2023-06-06
0.1 | Membuat pemodelan menggunakan Time Series ARIMA dan hasil implementasinya |  | Azka |  | 2023-06-07 | 2023-06-09 | 3 | 100% | 3 | bar: 2023-06-07 to 2023-06-09
0.1 | Mencoba membuat beberapa pemodelan menggunakan linear regression dan ANN |  | Nurulliza Camilla |  | 2023-06-08 | 2023-06-11 | 4 | 100% | 2
0.1 | Membuat pemodelan dengan algoritma XGBoost |  | Nurulliza Camilla |  | 2023-06-12 | 2023-06-14 | 3 | 100% | 3
4 | Data Visualisation |  |  |  |  | - |  |  | -
0.1 | Membuat Rancangan Visualisasi Tableau dengan Data Padi sebelum prediksi |  | Shintya |  | 2023-06-07 | 2023-06-10 | 4 | 100% | 3
0.1 | Membuat Visualisasi Data Prediksi Padi |  | Zeni |  | 2023-06-12 | 2023-06-12 |  | 100% | 1
5 | Technical Desain |  |  |  |  | - |  |  | -
0.1 | Membuat Desain PPT dan konten presentasi |  | Kevin |  | 2023-06-11 | 2023-06-13 | 3 | 100% | 2
-
-
-
Note on A7: ====== ID#AAAAvZ5ZOpY Vertex42 (2023-05-17 14:21:53) Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: ====== ID#AAAAvZ5ZOpg Vertex42 (2023-05-17 14:21:53) Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on D7: ====== ID#AAAAvZ5ZOpE Vertex42 (2023-05-17 14:21:53) Task Lead Enter the name of the Task Lead in this column.
Note on E7: ====== ID#AAAAvZ5ZOpM Predecessor Tasks (2023-05-17 14:21:53) You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on F7: ====== ID#AAAAvZ5ZOpA Vertex42 (2023-05-17 14:21:53) Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on G7: ====== ID#AAAAvZ5ZOpI End Date (2023-05-17 14:21:53) The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on H7: ====== ID#AAAAvZ5ZOpQ Vertex42 (2023-05-17 14:21:53) Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on I7: ====== ID#AAAAvZ5ZOpU Vertex42 (2023-05-17 14:21:53) Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on J7: ====== ID#AAAAvZ5ZOpc Vertex42 (2023-05-17 14:21:53) Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.